## Dashboard
Copyright - Sudharsan Iyengar - August 2017.
Tracking Project Work
| Team Name: | Ethan, Gunner, Will, Uzma |  |  |  | Member Contribution |  | Component Effort
| Project Description: | Card Game
| Activity | Time Spent | # of revisits to this activity | Output Artifact (formal and informal) | % of work done by due date | Team Member Name | Total time Spent | Component Name | Total time spent on component
| Understanding the problem | 4 hours | 12 |  | 100%
Creating a model for the solution
| Writing the Code using an IDE (initial) | 15 hours | 400 | Code | 75%
| Testing the code - number of runs | 10 hours | 600
Feedback from testing and completion

## Component Description
General Description of Components
Name of Component | Brief description of the Component | Team Members responsible
Deck | Contains all 52 cards that are initialized in the game | Uzma
Player | Contains all information regarding a player: their score, their hand, and the sum | Uzma, Will
Card | Storage class for a card | Uzma
GameState | Stores the state of the game and the total score. | Uzma
PlayerData | Has data used to transfer between Client to Server | Will
CardGameServer | Contains methos used to run the server | Will
Driver | Starts the program | Will
TestGui | Orginally meant for testing, but is now the GUI used to connect players to the game | Will
GameGUI | GUI for the card game | Ethan, Will
CardGame | Contains all the logic of game play. Initializes the players, creates a new deck, distributes cards from deck into hands, main play, and checks who is winning | Uzma

## Understanding the Problem
Understanding the Problem
Date | Component | Member Name | Time spent in minutes | Brief description of output
2018-09-14 | Decomposition of components of the game and how they work together | Uzma | 120 | We decided how to decompose the components and responsibilities
2018-09-03 | Game rules | Everyone | 80 | We looked over the rules for the game.
2018-09-20 | How the game will work | Everyone | 30 | Discussed what each of us should do and how
2018-10-03 | Discussed Progress | Everyone | 240 | Discussed progress and what we need to finish

## Creating the Model
Creating the Model
Date | Component | Member Name | Time spent in minutes | Brief description of output
2018-09-13 | Document | Will | 20 | Describing my classes
2018-09-16 | GUI Model | Will | 60 | Designed GUI model and how it should work

## Writing Code
Writing code
Date | Component | Member Name | Time spent in minutes | Brief description of output
00/14/18 - 09/18/18 | GamePlay logic | Uzma | 1080 | Wrote the actual code for the game play. Wrote the code for each of the components and how they interact with each other.
9/15/18- 10/2/18 | Networking | Will | 1770 | Worked on implementing the distrbuted game
10/6/18 - 10/7/18 | Implementation | Will | 380 | Made the game work with the GUI
2018-10-14 | Debugging | Will | 300 | Made the game more error proof

## Testing the code - # of runs
Testing the code - # runs per session
Date | Component | Member Name | Time spent in minutes | Brief description of output
| Networking | Will |  | I tested my networking stuff many times when writing the code

## Revisions based on Testing
Revisions based on Testing
Date | Component | Member Name | Time spent in minutes | Brief description of output